## Instructions
PhD Gantt Chart Template
By Resourceful Scholars' Hub
How to use this template
1. | Go to the "Gantt Chart" tab. Row 2 contains a 3-year monthly timeline (Jan 2026 – Dec 2028) — edit any month header if your program runs on a different schedule.
2. | In column A, replace the sample tasks with your own deliverables (modules, exams, proposal chapters, data collection, papers, conferences, dissertation chapters, viva).
3. | Choose a Category for each task from the dropdown in column B. This controls the bar colour on the timeline.
4. | Enter a Start Date and End Date for each task in columns C and D (blue cells = your input). Duration calculates automatically.
5. | Update the % Complete column (F) as you progress — this is for your own tracking and is not linked to the bars.
6. | The coloured bars in columns G onward appear automatically based on each task's start and end date — no manual formatting needed.
7. | Add more rows as needed. Select a fully formatted row, copy it, and paste into a new row to keep formatting and dropdowns consistent.
8. | Review and update this sheet monthly. A Gantt chart only helps if it reflects reality — revise dates as soon as something shifts.
Category colour legend
Coursework
Exams & Milestones
Proposal
Data Collection & Analysis
Writing
Conferences & Publications
Defense & Viva
Tip
Use this Gantt chart for your big-picture, multi-year plan, and pair it with a weekly to-do list for day-to-day execution. Read the full guide: resourcefulscholarshub.com/phd-gantt-chart/

## Gantt Chart
PhD Gantt Chart — 3-Year Timeline (edit tasks, dates & categories below)
Task | Category | Start Date | End Date | Duration (Days) | % Complete | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
Module 1 | Coursework | 2026-01-01 | 2026-03-31 | 90 | 0%
Module 2 | Coursework | 2026-04-01 | 2026-06-30 | 91 | 0%
Module 3 | Coursework | 2026-07-01 | 2026-09-30 | 92 | 0%
Module 4 | Coursework | 2026-10-01 | 2026-12-31 | 92 | 0%
Concept note | Exams & Milestones | 2026-06-01 | 2026-06-30 | 30 | 0%
Comprehensive exam | Exams & Milestones | 2026-12-01 | 2026-12-31 | 31 | 0%
Literature search & review | Proposal | 2026-09-01 | 2026-11-30 | 91 | 0%
Write Chapter 1 (Introduction) | Proposal | 2026-12-01 | 2026-12-31 | 31 | 0%
Supervisor review & revise Ch.1 | Proposal | 2027-01-01 | 2027-01-31 | 31 | 0%
Write Chapter 2 (Literature Review) | Proposal | 2027-02-01 | 2027-03-31 | 59 | 0%
Supervisor review & revise Ch.2 | Proposal | 2027-04-01 | 2027-04-30 | 30 | 0%
Write Chapter 3 (Methodology) | Proposal | 2027-05-01 | 2027-06-30 | 61 | 0%
Finalize proposal document | Proposal | 2027-07-01 | 2027-07-31 | 31 | 0%
Proposal defense | Exams & Milestones | 2027-08-01 | 2027-08-31 | 31 | 0%
Ethics approval application | Data Collection & Analysis | 2027-09-01 | 2027-09-30 | 30 | 0%
Data collection | Data Collection & Analysis | 2027-10-01 | 2027-12-31 | 92 | 0%
Data cleaning & analysis | Data Collection & Analysis | 2028-01-01 | 2028-02-29 | 60 | 0%
Journal article 1: draft & submit | Conferences & Publications | 2028-03-01 | 2028-03-31 | 31 | 0%
Conference 1: abstract & presentation | Conferences & Publications | 2028-04-01 | 2028-04-30 | 30 | 0%
Write dissertation Chapter 4 (Findings) | Writing | 2028-05-01 | 2028-06-30 | 61 | 0%
Write dissertation Chapter 5 (Discussion) | Writing | 2028-07-01 | 2028-07-31 | 31 | 0%
First full draft to supervisor | Writing | 2028-08-01 | 2028-08-31 | 31 | 0%
Journal articles 2 & 3: submit | Conferences & Publications | 2028-09-01 | 2028-09-30 | 30 | 0%
Conference 2: presentation | Conferences & Publications | 2028-09-01 | 2028-09-30 | 30 | 0%
Revise manuscript from feedback | Writing | 2028-10-01 | 2028-11-30 | 61 | 0%
Final formatting & compliance check | Writing | 2028-12-01 | 2028-12-15 | 15 | 0%
PhD Viva / Final defense | Defense & Viva | 2028-12-16 | 2028-12-31 | 16 | 0%